## Sayfa1
|  |  |  | March |  |  |  | April |  |  |  | May
Milestone 1 | CW/Tasks |  | Status | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
GitHub
| -repository creation |  | done
| -issue creation |  | done
| -Wiki document creation |  | done
| -Wiki update |  | cont.
First Django project
| -system set up installation |  | done
| -database creation with PostgreSQL |  | done
| -administration page creation |  | done |  | with sqlite
| -website view creation |  | done |  | with sqlite
| -advanced exercises |  | cont.
Project: co-learning platfrom
| Plan | -requirements eliciation | done |  |  |  | update
|  | -defining requirements | done |  |  |  |  | update
|  | -mockup designs | done
Milestone 2 | Design | -use case | todo
|  | -class | todo
|  | -sequence diagram preperation | todo
| Implementation | - continuous development | con.
Milestone 3 | Testing | -self testing | todo
|  | external testing | todo
Virtulization & Deployment